## Trang tính1
Members list
Lê Đình Cương
Nhung Quốc Bình
Trần Thanh Hải
Task ID | What to do | Assign to | Estimation |  | Actual |  | Done Criteria | Status | Note
|  |  | Start | End | Start | End
1 | Read through the DMS software SRS documentation to ask questions | Lê Đinh Cương | 2023-05-05 | 2023-05-06 | 2023-05-09 | 2023-05-09 | Write 8 questions | Done | Completed ahead of schedule
2 | Read through the DMS software SRS documentation to ask questions | Nhung Quốc Bình | 2023-05-09 | 2023-05-09 | 2023-05-09 | 2023-05-09 | Write 8 questions | Done | Completed ahead of schedule
3 | Read through the DMS software SRS documentation to ask questions | Trần Thanh Hải | 2023-05-09 | 2023-05-09 | 2023-05-09 | 2023-05-09 | Write 8 questions | Done | Completed ahead of schedule
4 | Read through the DMS software SRS documentation to ask questions | Lê Đinh Cương | 2023-05-09 | 2023-05-09 | 2023-05-09 | 2023-05-09 | Write 8 questions | Done | Completed ahead of schedule
5 | Write test cases for add defect function | Nhung Quốc Bình | 2023-05-10 | 2023-05-10 | 2023-05-10 | 2023-05-10 | Write 18 test cases | Done | Completed ahead of schedule
6 | Write test cases for add defect function | Trần Thanh Hải | 2023-05-10 | 2023-05-10 | 2023-05-09 | 2023-05-09 | Write 35 test cases | Done | Completed ahead of schedule
7 | Write test cases for add defect function | Nhung Quốc Bình | 2023-05-10 | 2023-05-10 | 2023-05-09 | 2023-05-09 | Write 24 test cases | Done | Completed ahead of schedule
8 | Write test cases for attach file function | Lê Đinh Cương | 2023-05-10 | 2023-05-10 | 2023-05-09 | 2023-05-09 | Write 25 test cases | Done | Completed ahead of schedule
9 | Write test cases for defect view or edit function | Nhung Quốc Bình | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2023-05-15 | Write 35 test cases | Done | Completed ahead of schedule
10 | Write test cases for defect view or edit function | Lê Đinh Cương | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2023-05-15 | Write 36 test cases | Done | Completed ahead of schedule
11 | Write test cases for defect list function | Nhung Quốc Bình | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2023-05-15 | Write 25 test cases | Done | Completed ahead of schedule
12 | Write test cases for defect list function | Trần Thanh Hải | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2023-05-15 | Write 35 test cases | Done | Completed ahead of schedule
13 | Write test cases for batch update defect function | Lê Đinh Cương | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2023-05-15 | Write 25 test cases | Done | Completed ahead of schedule
14 | Write test cases for batch update defect function | Trần Thanh Hải | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2023-05-15 | Write 25 test cases | Done | Completed ahead of schedule
15 | Write test cases for export defect function | Lê Đinh Cương | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2023-05-15 | Write 20 test cases | Done | Completed ahead of schedule
Test environment
Type | Test enviroment | Note
Hardware | Laptop, pc
Operating system | Win XP, Win 7, Win 10
Browser | Chrome, Cốc Cốc, Microsoft Edge | Latets version
Connect | LAN, wifi